## ProjectPlan_Week03
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
BKJGRID_8kCuJsyhuIyOGMgAFUAe | Requirement Gathering | Initiating | Not started | Medium | ALICIA GOH TING TING;FAREEN NATHRAH BINTI YUSRI;HOR YING HUAI;SITI NUURIN HAYATI BINTI MURAN TURKEY | HOR YING HUAI | 10/27/2025 | 10/06/2025 | 10/10/2025 | false | true
iITMbmgWKUieP7KulGrSU8gAExMW | Data Collection | Planning | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY;ALICIA GOH TING TING;FAREEN NATHRAH BINTI YUSRI;HOR YING HUAI | HOR YING HUAI | 10/27/2025 | 10/13/2025 | 10/17/2025 | false | true
hX-LY-dOw0GGEBHRYu9HCMgAK2qJ | Model Design | Planning | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY;ALICIA GOH TING TING;FAREEN NATHRAH BINTI YUSRI;HOR YING HUAI | HOR YING HUAI | 10/27/2025 | 10/20/2025 | 10/24/2025 | false | true
fbQb7cf6DUiOHxNEFBc-qsgAOiBp | Model Training | Executing | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY;ALICIA GOH TING TING;FAREEN NATHRAH BINTI YUSRI;HOR YING HUAI | HOR YING HUAI | 10/27/2025 | 10/27/2025 | 10/31/2025 | false | false
yooVYrWTGkmgpQF6obwAg8gAJ-sL | Model Evaluation | Executing | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY;FAREEN NATHRAH BINTI YUSRI;HOR YING HUAI;ALICIA GOH TING TING | HOR YING HUAI | 10/27/2025 | 11/03/2025 | 11/07/2025 | false | false
4njHAPtblEq0JF974z7cmcgANqT4 | Dashboard Development | Executing | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY;ALICIA GOH TING TING;FAREEN NATHRAH BINTI YUSRI;HOR YING HUAI | HOR YING HUAI | 10/27/2025 | 11/10/2025 | 11/14/2025 | false | false
sqE6Gqge4kWJKVdZN6zA48gADk0S | Testing & Validation | Monitoring and controlling | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY;ALICIA GOH TING TING;FAREEN NATHRAH BINTI YUSRI;HOR YING HUAI | HOR YING HUAI | 10/27/2025 | 11/17/2025 | 11/21/2025 | false | false
5KghJeGPZkSYpZ7_KfpsCsgAFvBu | Report & Presentation | Closing | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY;ALICIA GOH TING TING;FAREEN NATHRAH BINTI YUSRI;HOR YING HUAI | HOR YING HUAI | 10/27/2025 | 11/24/2025 | 11/28/2025 | false | false

## ProjectPlan_Week03 (Plan name)
Plan name | AI Project Management
Plan ID | 0nxfOMIZrUai7OIrGsvT9sgAAI1i
Date of export | 10/27/2025

## WBS_Week04
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
VlAMWqfo_0SdUNYQdR5aXMgAOz6i | Define functional and non-functional requirements | Requirement Gathering | Not started | Medium | FAREEN NATHRAH BINTI YUSRI | HOR YING HUAI | 11/07/2025 | 10/09/2025 | 10/10/2025 | false | true |  |  |  |  | Milestones
i4GdWDCgC0mQujbbEbWaGMgAM48l | Gather sample user commands for NLP intent recognition | Data Collection | Not started | Medium | ALICIA GOH TING TING | HOR YING HUAI | 11/07/2025 | 10/11/2025 | 10/13/2025 | false | true
Dob_BArrLkSVpG5dGFq308gAHiOE | Collect and prepare dataset for model training (intent and entity samples) | Data Collection | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY | HOR YING HUAI | 11/07/2025 | 10/14/2025 | 10/17/2025 | false | true |  |  |  |  | Milestones
vNUHwLEFTEWcCx3F1uG1NcgAJJgy | Define input features and output classes for task commands | Model Design | Not started | Medium | FAREEN NATHRAH BINTI YUSRI | HOR YING HUAI | 11/07/2025 | 10/22/2025 | 10/24/2025 | false | true |  |  |  |  | Milestones
ldESFVd8Q0ymf3CDRI_LaMgAGU0U | Design model structure for intent recognition | Model Design | Not started | Medium | HOR YING HUAI | HOR YING HUAI | 11/07/2025 | 10/18/2025 | 10/21/2025 | false | true
0lWQIo1MQEKt3pjKregD68gAB2py | Fine-tune entity extraction model | Model Training | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY | HOR YING HUAI | 11/07/2025 | 10/29/2025 | 10/31/2025 | false | true |  |  |  |  | Milestones
5T3bJ6_6p0ymEYVmWHN4YcgAEb42 | Compare model results and select best-performing model | Model Evaluation | Not started | Medium | FAREEN NATHRAH BINTI YUSRI | HOR YING HUAI | 11/07/2025 | 11/05/2025 | 11/07/2025 | false | false |  |  |  |  | Milestones
OqFwjn2rzkOOmPTlhmnglcgAH4Na | Identify user needs and system objectives | Requirement Gathering | Not started | Medium | HOR YING HUAI | HOR YING HUAI | 11/07/2025 | 10/08/2025 | 10/09/2025 | false | true
jcbD7n4mJ0CTkfL4WUW7WMgAFdAO | Train intent recognition model using collected dataset | Model Training | Not started | Medium | ALICIA GOH TING TING | HOR YING HUAI | 11/07/2025 | 10/25/2025 | 10/28/2025 | false | true
-RxYOlpe10Gg0aeofLqQ48gAFn7T | Evaluate model accuracy and precision | Model Evaluation | Not started | Medium | HOR YING HUAI | HOR YING HUAI | 11/07/2025 | 11/01/2025 | 11/04/2025 | false | true
9tj0HAl1HECKTerR9X2mb8gAO05L | Integrate Telegram bot with backend and model API | Dashboard Development | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY | HOR YING HUAI | 11/07/2025 | 11/12/2025 | 11/14/2025 | false | false |  |  |  |  | Milestones
RxunljTZ7EKXOI2YGMFvBMgAOnsC | Develop Streamlit dashboard interface | Dashboard Development | Not started | Medium | ALICIA GOH TING TING | HOR YING HUAI | 11/07/2025 | 11/08/2025 | 11/11/2025 | false | false
LviEagxgzEeJ0SQajupFJcgAAGiw | Validate usability with sample users | Testing and Validation | Not started | Medium | FAREEN NATHRAH BINTI YUSRI | HOR YING HUAI | 11/07/2025 | 11/19/2025 | 11/21/2025 | false | false |  |  |  |  | Milestones
-aLBO3ZXY0-phg14NoGrBcgAMfVO | Conduct functionality testing (bot, dashboard, reminders) | Testing and Validation | Not started | Medium | HOR YING HUAI | HOR YING HUAI | 11/07/2025 | 11/15/2025 | 11/18/2025 | false | false
mAOkziW5K0-7tNbdrwNvNcgAJjqC | Submit final deliverables to ULearn and GitHub | Report and Presentation | Not started | Medium | SITI NUURIN HAYATI BINTI MURAN TURKEY | HOR YING HUAI | 11/07/2025 | 11/27/2025 | 11/28/2025 | false | false |  |  |  |  | Milestones
vNqsexEY60eJJi4xlecHGsgACbMU | Prepare project report and presentation slides | Report and Presentation | Not started | Medium | ALICIA GOH TING TING | HOR YING HUAI | 11/07/2025 | 11/22/2025 | 11/26/2025 | false | false

## WBS_Week04 (Plan name)
Plan name | WBS_Week04
Plan ID | BfMgSHat3k64ec5bX5Np-cgAFmHP
Date of export | 11/07/2025